## Slide 1: Oriel Board update 28 April 2022

## Slide 2: Overview
Context
  Reminder of the Oriel programme
Preparation for Full Business Case (FBC)
  NHS assurance to FBC
Key risks

## Slide 3: Oriel timeline
2017
20222
2011/12
MEH, UCL and MEC joint partnership established
Options analysis
2013/14
Site search and negotiation
Refreshed strategic outline case approved
RIBA design competition launched
Options agreement signed
Developing outline business cases
2019
Design team appointed
NHS public consultation
Developing outline business cases
2020
Commissioners approve NHS service relocation
Planning application submitted
NHS outline business case approved
2021
UCL full business case approved
Marketing for sale of City Road Island site & confirmation of preferred developer
Resolution to grant planning approval
Moorfields full business case approvals
Site enabling works
2018
2015/16
Public engagement
Strategic outline case approved
2023
Main construction
2026
New centre opens
Notes:   Development of Oriel proposal initiated in 2012 to consider future options for the delivery of eye care, research and education.
  Between 2013 and 2019, five phases of engagement took place about our proposed move and the options available including relocation to the St Pancras hospital site.
  Design team selection in 2019 following RIBA competition.
  Service change public consultation programme 2019 indicated broad support for our proposed move from City Road to a new centre (73%).
  In February 2020, clinical commissioners approved the proposal to create a new centre.
  Moorfields Outline Business Case (OBC) submitted in February 2020.
  Oriel confirmed as one of the New Hospital Programme (NHP) schemes announced by the Prime Minister in October 2020.
  Planning application submitted to Camden Council in October 2020.
  Moorfields OBC approved in December 2020.

## Slide 4: NHS assurance to FBC
We have received confirmation that the following have now been approved by our regulators;
  Joint Development Vehicle business case
  Land Disposal business case
  OBC financial case affordability addendum
We are still awaiting feedback from the New Hospital Programme (NHP) team’s In Flight Project Review

## Slide 5: Key risks
Risk | Mitigation | Update
Revenue position for 2022/23 not finalised until mid-April – risk that FBC submission is delayed | Active engagement with NCL and NHSE/I to clarify 2022/23 position Active engagement with NHSE/I and DHSC on timelines for business case submission and approval dates | Engagement ongoing
City Road disposal – risk that bids are not in line with site valuations | Completion of City Road disposal process and confirmation of preferred bidder, with confirmed price by December 2021 | Land Disposal case approved by regulator
Regulator decision making – risk that Moorfields business case is delayed | Active engagement with NHSE/I, DHSC and HMT on timelines for business case submission and approval dates | Engagement ongoing
Securing St Pancras site vacant possession – risk that this is delayed | Active engagement with Camden & Islington; NCL ICS; London Region team | Engagement ongoing
Contractor procurement – risk that tender prices do not align with OBC assumptions | Completion of contractor procurement process and confirmation of preferred bidder, with confirmed price by December 2021 | Final tender report and recommendation to be considered at April trust board