## Slide 1: Oriel Board update 26 May 2022

## Slide 2: Overview
The Oriel programme
Submission of the Full Business Case (FBC)
National Hospital Programme visit
Key risks

## Slide 3: Oriel timeline
2017
20222
2011/12
MEH, UCL and MEC joint partnership established
Options analysis
2013/14
Site search and negotiation
Refreshed strategic outline case approved
RIBA design competition launched
Options agreement signed
Developing outline business cases
2019
Design team appointed
NHS public consultation
Developing outline business cases
2020
Commissioners approve NHS service relocation
Planning application submitted
NHS outline business case approved
2021
UCL full business case approved
Marketing for sale of City Road Island site & confirmation of preferred developer
Resolution to grant planning approval
Moorfields full business case approvals
Site enabling works
2018
2015/16
Public engagement
Strategic outline case approved
2023
Main construction
2026
New centre opens
Notes:   Development of Oriel proposal initiated in 2012 to consider future options for the delivery of eye care, research and education.
  Between 2013 and 2019, five phases of engagement took place about our proposed move and the options available including relocation to the St Pancras hospital site.
  Design team selection in 2019 following RIBA competition.
  Service change public consultation programme 2019 indicated broad support for our proposed move from City Road to a new centre (73%).
  In February 2020, clinical commissioners approved the proposal to create a new centre.
  Moorfields Outline Business Case (OBC) submitted in February 2020.
  Oriel confirmed as one of the New Hospital Programme (NHP) schemes announced by the Prime Minister in October 2020.
  Planning application submitted to Camden Council in October 2020.
  Moorfields OBC approved in December 2020.

## Slide 4: Approval and submission of the Oriel FBC
The trust board approved the Oriel FBC at its extraordinary public board meeting on 13 May
The trust membership council approved four significant transactions in relation to Oriel at its extraordinary public meeting on 13 May
  Approve the Full Business Case
  Exercise the Option Agreement to purchase 2 acres of land on the St Pancras Hospital site
  Establish a Joint Development Vehicle with UCL
  Enter into a c£300m contract with the preferred bidder to construct Oriel
NCL CCG strategy and commissioning committee confirmed their support of the Oriel FBC at their meeting on 19 May
The Oriel FBC was formally submitted to NHSE/I and NHP on 19 May

## Slide 5: National Hospital Programme
The government has committed to 40 new hospitals across England by 2030, backed by an initial £3.7 billion of investment
These will provide better care for patients, an improved working environment for staff and help the NHS reach its net zero carbon ambition
Currently, the national programme comprises eight pre-existing schemes and 40 new hospitals, totalling 48 hospitals
In October 2020, the government named 32 hospitals which will form part of the 40 new hospitals and is now calling for NHS Trusts to submit their expressions of interest to be one of the further eight hospitals.
The New Hospital Programme is a joint Department of Health & Social Care and NHS England & NHS Improvement central team. It has been set up to lead the delivery of the new hospitals, working closely with all NHS trusts involved. This includes how they phase the building programme so they can work with similarly developed trusts to maximise the benefit for other schemes
Oriel is one of the named 32 hospitals included in the National Hospital Programme and is considered a Phase One “in-flight” scheme

## Slide 6: National Hospital Programme visit
On 19 May, the National Hospital Programme team visited the City Road site
The purpose of their visit was to
  learn more about the progress of Oriel, our new integrated centre in St Pancras and to tour the trust’s existing City Road site
  understand any learnings the Oriel team have that would be useful for other hospital builds in different phases of the NHP
The visit team include Natalie Forrest (NHP SRO) and Morag Stuart (NHP chief programme officer)
We are still awaiting feedback from the New Hospital Programme (NHP) team’s In Flight Project Review

## Slide 7: Key risks
Risk | Mitigation | Update
Revenue position for 2022/23 not finalised until mid-April – risk that FBC submission is delayed | Active engagement with NCL and NHSE/I to clarify 2022/23 position Active engagement with NHSE/I and DHSC on timelines for business case submission and approval dates | Commissioners and NHSE/I have agreed the basis of the submitted financial case
City Road disposal – risk that bids are not in line with site valuations | Completion of City Road disposal process and confirmation of preferred bidder, with confirmed price by December 2021 | Land Disposal case approved by regulator
Regulator decision making – risk that Moorfields business case is delayed | Active engagement with NHSE/I, DHSC and HMT on timelines for business case submission and approval dates | Engagement ongoing
Securing St Pancras site vacant possession – risk that this is delayed | Active engagement with Camden & Islington; NCL ICS; London Region team | Engagement ongoing
Contractor procurement – risk that tender prices do not align with OBC assumptions | Completion of contractor procurement process and confirmation of preferred bidder, with confirmed price by December 2021 | Final tender report approved at Oriel Joint Executive Board Likely to be key area of Regulator review